## Portal TOC
Project OSHS
Table of Contents
Team | Team - directory with roles and responsibilites
Action Items | Action Items - Log of Asks
Risks & Issues | Risks & Issues - Log of Risks and Issues
Schedule | Schedule - High-level plan of project milestones and deliverables
Meetings | Meeting Minutes

## Team
Team & Stakeholders
Name | Role on the Project | Responsibilities | Email | Phone
Project Execution Team
Noble | Lead | Lead, Sales, Adminstration, Jv's, Finance
Dileep |  | Product development
Shivakumar |  | Operations
Rajeev |  | Product development
Bopanna |  | App Development

## Milestone Schedule
Milestone Plan
Product Development schedule and Hierarchy | [7 empty] | Delivery time lines and status
Sl # | Activity /Deliverable / Milestone | Owner(s) | % Complete | Status | Start | Plan End | Actual End | 2018-05-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
1 | Create a Super Admin
| Ability to create City and Zones within cities |  |  |  | 23/04/18 | 31/05/18
| Create a community |  |  |  | 23/04/18 | 31/05/18
| Upload all details of the residents (Create a template on all the required details for residents) |  |  |  | 23/04/18 | 31/05/18
| Ability to create a Community Admin (Apartment Manager and Association) Create a Role and responsibility document |  |  |  | 23/04/18 | 31/05/18
| Abiity to make bulk uploads of community details through Excel |  |  |  | 23/04/18 | 31/05/18
| Ability to provide and remove previlages and access as required by the association members to residents and Manager |  |  |  | 23/04/18 | 31/05/18
2 | Create a Heirarchy from Country, City and Zone
| The Heirarchy should start from Region/Section/Zone | Dileep | 100 | Complete
| Ability to give a superadmin previlages to different individuals for each zones or one individaul managing multiple zones based on the requirement |  |  |  | 23/04/18 | 31/05/18
| Create work flow Diagrams | Noble |  |  | 23/04/18 | 31/05/18
3 | Create a community
| Community name | Dileep
| Location on Maps | Dileep
| Block names | Dileep
| Amenities | Dileep
| Name of the resident, mapped to flat number, block, mobile number Name of the family members with date of birth, rented or owner, Number of parking slots, vechicle details, Maids, Maid names , Maid phone numbers, picture)(replicate the same for Driver, cooks and baby sitters) | Dileep
| Map residents who are with association and and provide special previlages eligible | Dileep
| Map the amenities with details | Dileep
| Community Directory with Name, Phone number, Flat number, block name/number | Dileep
4 | AMC list
List of equipements that require AMC
Equipment details
OEM details like POC Name, Phone Number, AMC schedule, reminder with message, completion updates with mails,
AMC contract details and documents soft copy
AMC Schedule
5 | Vendor List
Ability to create a vendor profile with name, Product name, mobile number, land line number, Address, Email id, Website details, Soft copy of documents for AMC and other services and contract
6 | Ticketing system
List of different tickets to be created
Create a workflow for each type of ticket
List the different areas required in a ticket
Mapping the ticket to resident, block, community, zone and city
Ability to provide feedback for each ticket and ability to build reports for each of the tickets based on each of the areas in the ticket
7 | Association details
Option to provide a special previlage for residents if they are part of the association
List the privilages of an association member
Ability to send a message only to the assoction group for the residents and within the association members
Ability to add and remove the association privilages for residents
Ability to change the community admin and add new admin
Add the title, President, secretary, treasurer, members etc
8 | Communication
Notice Board for all residents
ability to post community pictures by date
Ability to message or have conversations
Ability to conduct surveys, decide the survey models, weightage, calculation
Ability to conduct online elections for associations
9 | Visitor Management
Create a feature to send notification to resident with Visitor pictures, Name, phone Number and purpose from the security gate
Ability to schedule visitors with name, Phone number, time, date of arrivals, arrival notification etc by the residents
Map The Maids/Driver/Cook/Baby Sitter to all the flats they work and the timing alloted for them, with the ability to change the time by the resident, if there is overlapping time between flats throw an error and ask to choose a different time slot.
Ability to remove access to the maids/Driver/Cook/baby sitter by the resident
10 | Amenities Booking
Ability to book party hall for two slots in a day Lunch (9.00 AM to 4.00 PM)and Dinner(5.00 PM to 11.00 PM)
Similar to Outlook calendar
Residents needs to block the date and time required, triggers a notification to Community admin or Association POC (both features required for operational felxibility). Once it is approved the date and time is highlighted and others will not be able to book the same. This calendar can be viewed by all all in the community. This should be real time.
11 | Documentation
Vendor List, contract, Building plan and details in soft copy,
Work flow SOPS for equipments
Association Rule book. Create a space to upload documents for the below with Naming convention Maids/Drivers/Cooks, Baby Sitter. Visitor Management and Parking Maintenance fees and last date Garbage Clearance Party Hall, Gym, Swimming pool, Amenities rules
12 | Reporting
Ability to pull reports at the lowest level (community) to a country, with ability to break down at each community and apartment
13 | Accounting
Track all Expenses and Incomes
Payment gateway option
Attach Receipts to all expences
Reporting by day, month and year.
Tax Computation

## Action Items
Open Action Items
** Hover over column heading to see values or description
** Status column is auto formated based on the value - hover over Status column to see desc of values
Item # | Status | DESCRIPTION | OWNER - Assigned To | Open Date | Due Date | Date Closed | Current Status / Resolution
1 | Complete | Dileep to share Github Access | Dileep | 19/05/2018 | 21/05/2018 | 20/05/2018
2 | Complete | Explore Data modelling tool and share. Dileep and rajeev to finalize | Dileep and rajeev to finalize | 19/05/2018 | 21/05/2018 | 22/05/2018 | Rajeev to use Modelio.org data modelling tool a free version, it could be used for process flow too
3 |  | Build and upload the data model (Community) to the Github account | Rajeev | 19/05/2018 | 28/05/2018 |  | Rajeev and Dileep to build the Data model for Create community section in milestone tab, refer Noble's apartment adda account for reference. Login credentials available in Credentials tab
4 |  | Complete the Ticketing system process flow | Noble | 19/05/2018 | 28/05/2018
5 |  | Rajeev, Dileep and Noble to meet at 7.30 AM 22nd May | All | 19/05/2018 | 21/05/2018
6 |  | Rajeev and Dileep to connect on Saturday | Dileep/Rajeev | 26/05/2018 | 26/05/2018
7 |  | Rajeev, Dileep and Noble to meet at 7.30 AM 29th May | All | 19/05/2018 | 29/05/2018
8 |  | Rajeev to update the milestone with modifications we discussed on 29th | Rajeev |  | 2018-05-06
9
10
11
12
13
14
Closed Action Items
Item # | Status | DESCRIPTION | OWNER - Assigned To | Open Date | Due Date | Date Closed | Current Status / Resolution

## Work Flow
SL # | Workflow List | Phase 1 Developement | Phase 2 Developement
1 | Communications | Ticketing systems | Gate keeping
2 | Ticketing systems | Facility Booking | Apartment Staff Attendance
3 | Facility Booking | Communications/Notice board | Community Documents
4 | Payment Gateway | Payment Gateway | Activities listing and Management
5 | Gate keeping | Association Privileges | Chat Room features and options
6 | Apartment Staff Attendance
7 | Chat Room
8 | Activities listing and Management
9 | Community Documents
10 | Association Privileges
11 | Retail
12 | Laundry
13 | Car Wash
14 | Food delivery/Tiffin Services
15 | Maintenance

## Meeting Minutes
Meeting Minutes
Dileep to create a clould account | Done
Dileep to create database by next week by 4th | Done
Meeting Minutes
create a seperate table for party hall booking, with Admin and Association ability to see the booker information
Hall booking to have payment tracking but no online payment option. (Should we provide a Payment gateway option)
Portal to show charges and cancellation charges involved
Association also to be added as a member for booking classes like dance/karate etc. The third party will be charged and charges will be different than for the residents
Feature on calendar to opt for food catering vendor
Photographer and Videographer booking option. Cake/Decoration/Lights and PA/Chairs as extra options. Option to request association assistance...
Dileep to explore retail/E commerce , Laundry, Food delivery, Auto Wash options
Meeting Minutes (23/04/2018)
Focus on developing the Community Management platform
Deliberate on our E-commerce Business Model We will not be offering any incentives for Association or Managers Will recruit a dedicated delivery and service boy for every 500 home units
Noble to create work flow diagrams
Meeting Minutes (19/05/2018)
rajeev to explore new data modelling tool, that is flexible in future
Dilleep to share the Github access details and update the same in The Project tracker
As per plan, team to meet three times a week
Dileep to share the Data model built by him to Rajeev for reference
Noble to complete the Ticketing system Process flow, Stakeholders and features
Meeting Minutes (22/05/2018)
Rajeev to use Modelio.org data modelling tool a free version, it could be used for process flow too
Rajeev and Dileep to build the Data model for Create community section in mile stone
Rajeev and Dileep to connect on Saturday to review and make changes to the data model, if required. Finalize the Data model for Section three"Create community" Please refer Appartment adda we want all of the features they have for sure.
Meeting Minutes (29/05/2018)
Update Model so that Owner can be person or organization
Update Model so that Maintainence fee can be tracked
Update Model so that Amenity is optionally linked to block
Update Model so that Membership to community not required
Update Model so that Association link to tenant is optional with role
Meeting Minutes (06/06/2018)
Model to include Tenant Book-keeping [Rajeev]
Model to include Tenant Vehicle Registry [Rajeev]
Model to include Visitor Management [Rajeev]

## Credentials
Name | User id | Password
Shopify | dileepkrishnan@gmail.com | India123.com
Azure | noblepr@outlook.com | Anjana_salok1
Github | facitechrepo@gmail.com | India123.com
Apartment adda | Login - 9845971074 | Anjana_salok1

## Risks & Issues
Risk Management Plan Tracking (RMPT)
[9 empty] | Risk Response Plan (RRP) |  | Risk Likelihood
Track # | Issue or Risk | Condition | Risk / issue Description | Potential Impact | Owner | Open Date | Target Resolution Date | Close Date | Mitigation Plan (Description of actions that the project will take to ensure that the risk is averted) | Contingency Plan (Description of actions that the project will take if the risk is realized) | Probability (0-3) | Impact (0-3) | Risk Rating (Prob*Impact) | Status / Comments
0
0
0
0
0
0
Closed Risks / Issues
0
0
0
0
0
0

## Vegetables Pricing
June 10th |  | Wholesale Market Price |  |  |  |  | BIG Basket |  |  | Retail Market price |  |  | Star Market
Sl# | Name | Price | Quantity | Pcs Approx | Qty | Per Kg/Pcs price | BB Price | Difference Amt | % Difference | Per Kg/Pcs price | Difference Amt | % Difference | Per Kg/Pcs price | Difference Amt | % Difference
1 | Cauliflower | 350 | sack | 20-25 | 1 Pc | 17.5 | 24 | 6.5 | 37.1429 | 30 | 12.5 | 71.4286
2 | Cabbage | 250 | sack | 20-25 | 1 Pc | 12.5 | 25 | 12.5 | 100 | 20 | 7.5 | 60 | 12 | -0.5 | -4
3 | Ladies finger | 20 | 1 Kg | 1 Kg | 1 Kg | 20 | 18 | -2 | -10 | 40 | 20 | 100 | 25 | 5 | 25
4 | Tomatoes 1st Quality | 250 | BOX | 15 Kg | 1 Kg | 16.6667 | 32 | 15.3333 | 92 | 15 | -1.6667 | -10
5 | Tomatoes 2nd Quality | 200 | BOX | 15 Kg | 1 Kg | 13.3333 | 27 | 13.6667 | 102.5 | 12 | -1.3333 | -10 | 10 | -3.3333 | -25
6 | Tomatoes 3rd Quality | 150 | BOX | 15 Kg | 1 Kg | 10 | 22 | 12 | 120 | 10 | 0 | 0
7 | Ridge Guard | 450 | 50 | 50 Pcs | Pc | 9 | 9 | 0 | 0 | 60 | 51 | 566.6667
8 | Drumstick | 400 | 100 | 100 | 1 Pc | 4 | 7 | 3 | 75 | 6 | 2 | 50
9 | raddish | 100 | 5Kg | 5Kg | 1 Kg | 20 | 25 | 5 | 25 | 60 | 40 | 200
10 | Capsicum 1st Quality | 200 | sack | 10kgs | 1 Kg | 20 | 99 | 79 | 395 | 60 | 40 | 200 | 45 | 25 | 125
11 | Capsicum 2nd Quality | 400 | sack | 15kgs | 1 Kg | 26.6667 | 50 | 23.3333 | 87.5 | 40 | 13.3333 | 50
12 | Kholrabi.Nukol | 200 | Sack | 25 Kgs |  | 8 |  | -8 | -100 | 40 | 32 | 400 | 49 | 41 | 512.5
13 | Brinjal | 350 | 40 Sack | 40 Kgs | 1 Kg | 8.75 | 56 | 47.25 | 540 | 40 | 31.25 | 357.1429 | 35 | 26.25 | 300
14 | Beans | 800 | sack | 40 Kgs | 1 Kg | 20 | 149 | 129 | 645 | 80 | 60 | 300 | 89 | 69 | 345
15 | Bitter Gourd | 350 | Box | 8 Kgs | 1 Kg | 31.25 | 39 | 7.75 | 24.8 | 80 | 48.75 | 156 | 69 | 37.75 | 120.8
16 | Beetroot | 400 | 20 kgs | 20 Kgs | Kg | 20 | 30 | 10 | 50 | 40 | 20 | 100 | 25 | 5 | 25
17 | Carrot | 150 | sack | 10 Kgs | 1 Kg | 15 | 34 | 19 | 126.6667 | 60 | 45 | 300 | 70 | 55 | 366.6667
18 | Chilli | 500 | sack | 10 Kgs | Kg | 50 | 36 | -14 | -28 | 80 | 30 | 60
19 | Cucumber | 250 | sack | 20 Kgs | 1 Kg | 12.5 | 32 | 19.5 | 156 | 30 | 17.5 | 140
20 | Lemon | 80 | 1 Kg | 1 Kg | 1 Kg | 80 | 99 | 19 | 23.75 | 80 | 0 | 0 | 89 | 9 | 11.25
21 | Snakegourd long/Big 3 ft long | 200 | 14 Pcs | 14 Pcs | 1 Pc | 14.2857 | 32 | 17.7143 | 124 | 20 | 5.7143 | 40
22 | Ginger | 850 | 10 Kgs | 10 Kgs | 1 Kg | 85 | 165 | 80 | 94.1176 | 120 | 35 | 41.1765
23 | Mint/Pudina | 5 | 1 Bunch | 1 Bunch | 1 Bunch | 5 | 15 | 10 | 200 | 20 | 15 | 300
24 | Corriander Natti | 35 | 1 Bunch | 1 Bunch |  | 35 |  | -35 | -100 | 50 | 15 | 42.8571
25 | Corriander Normal | 20 | 1 Bunch | 1 Bunch | 1 Bunch | 20 | 24 | 4 | 20 | 40 | 20 | 100
26 | Spinach | 100 | 15 Bunch | 15 Bunch | 1 Bunch | 6.6667 | 20 | 13.3333 | 200 | 20 | 13.3333 | 200
27 | Curry Leaves | 50 | Big bunch | 15 - 20 Small bunches | 1 Bunch | 3.3333 | 36 | 32.6667 | 980 | 10 | 6.6667 | 200
28 | Raw Mango | 600 | Sack | 30 Kgs | 1 Kg | 20 | 30 | 10 | 50 | 40 | 20 | 100 | 26 | 6 | 30
[6 empty] | 604.4524 | 1135 |  |  | 1203 |  |  | 544
|  |  |  | BIg Basket |  | Average per Unit Difference | 530.5476
[6 empty] | Average per Unit % Difference | 87.7733
|  |  |  | Market Retail |  | Average per Unit Difference | 598.5476
[6 empty] | Average per Unit % Difference | 99.0231
|  |  |  | Star Market |  | Average per Unit Difference | 530.5476
Average per Unit % Difference

## Use Cases
Epic | Story Number | Description | User
Community Management | 1 | As a user i want to be able to register a community in the application. 1. Each community is identified by a unique name. 2. A community should specific a general locality or location. 3. A community can have one or more contacts associated with it. | Application User/Admin
Community Management | 2 | As a user i want to be able to register an apartment and associate it to a community. 1. Each Apartment is identified by a unique name. 2. An apartment must have a specific location. 3. A Section may be associated with one or more contacts 4. An apartment may be associated with one or more phone numbers and each identified by a label. 5. An apartment must belong to a specific community | Application User/Admin
Community Management | 3 | As a user i want to be able to register one or more sections against an apartment. 1. Every apartment should contain atleast one section. Sections can be used to represent Blocks. 2. Every Section must be associated to an Apartment 3. Every Section is identified by a unique name in the scope of that apartment 4. A Section may be associated with one or more contacts 5. A Section may be associated with one or more phone numbers and each identified by a label | Application User/Admin
Community Management | 4 | As a user i want to be able to register one or more units against a section. 1. Every Section should contain atleast one unit. 2. Every Unit is identified by a unique name/number in the scope of that Section. 3. A Unit must be associated with one owner contact. 4. A Unit must be associated with one or more tenants. 5. A Unit must track the status of its maintainence fee. | Application User/Admin
Amenity Management | 5 | As a super user i want to be able to register an amentity against a community or an apartment. 1. An amenity should have a unique name within the scope of the community or apartment 2. An amenity should have a detailed description. 3. An amenity should define an availability schedule it applicable 4. An amenity should define pricing if applicable 5. An amenity should define capacity if applicable | Application Admin
Association Management | 6 | As a user i want to be able to register an association. 1. An association must be tied to a community or an apartment. 2. An association must have multiple contacts linked to it and each must define a role. 3. An association may be linked to multiple documents | Application User/Admin
Community Management | 7 | As a user i want to be able to register one or more tenants against a unit. 1. Atleast one of the tenants mut be marked as primary. | Application User/Admin

## Dev Guidelines
Number | Title | Description | Applies to
1 | Audit & Record Management | Every database entity must contain the following fields in addition to the fields that represent the entity 1. Created 2. Created by 3. Updated 4. Updated by 5. Active 6. UUID 7. Tags 8. Comments | Database